## Sheet1
Detail of Infrastructure Development Projects at MC Vehari (2022-23)
Sr. No. | Project Name | Cost (Rs. Millions) | Consultant | Current Status
1 | Improvement and Rehabilitation of Jinnah Road, Zoo Road and Gol Chowk in Vehari City | 150.923 | JERS | Letter sent to Contractor for Deposit of 10% Additional Performance vide letter no. 200/MO(I)/CO/MC- VR dated 20-05-2023
2 | Improvement and Rehabilitation of Muhammadi Bakery Road in Vehari City | 60.43 | JERS | Letter sent to Contractor for Deposit of 10% Additional Performance vide letter no. 201/MO(I)/CO/MC- VR dated 20-05-2023
3 | Improvement and Rehabilitation of Sharqi Colony Road and Seed Farm Road in Vehari City | 131.437 | JERS | Letter sent to Contractor for Deposit of 10% Additional Performance vide letter no. 202/MO(I)/CO/MC- VR dated 20-05-2023
4 | Improvement and Rehabilitation from Railway Crossing to canal Road and Club Road to Chungi No.6 & People colony road in Vehari City | 158.728 | JERS | Letter sent to Contractor for Deposit of 10% Additional Performance vide letter no. 203/MO(I)/CO/MC- VR dated 20-05-2023
| Roads + Chowks | 64.28 | JERS | PC-I with PMDFC
5 | Parking Shed | 35.924 | JERS | Letter forwarded to DGPR for Publication in Newspapers
6 | Water Supply | 1531 | Asian | Pending from Consultants
| Total | 2132.722